GitHub Enterprise → GitHub EU

Full Migration Plan

Design · Gap Analysis · Infrastructure · Data Upload Prevention · Execution Plan · Team Engagement · Templates

UK Regulated Bank  ·  ~250 Repos  ·  Data Science Heavy  ·  Cloud Build CI  ·  ACG Governance

Author: (you)  ·  27 April 2026  ·  v1.0 Final

| Part | Sections | Contents |
| --- | --- | --- |
| 1 — Context & Gaps | 1–5 | What we have, what we are moving to, Cloud Build question, gap analysis, open decisions, what transfers cleanly |
| 2 — Post-Migration Design | 6–8 | GitHub EU org structure, ACG steady state, day-to-day experience, data upload prevention design, governance policy |
| 3 — Execution Plan | 9–10 | Migration phases 0–4, master timeline, phase details, wave runbook, validation checklists, rollback procedures |
| 4 — Team Engagement | 11–13 | Dependency tiers D1–D4, data science special handling, platform team relationship |
| 5 — Communication | 14–15 | Communication plan and timeline, per-tier engagement plans step by step |
| 6 — Risks, Gaps & Done | 16–18 | Risk register, gaps tracker, definition of done |
| 7 — Templates | 19–23 | T−7 notifications (3 versions), weekly status report, meeting log, decisions & actions log, team register |

PART 1

Context & Gap Analysis

What we have, what we are moving to, and every gap mapped

# 1. What We Are Doing and Why

We are migrating approximately 250 repositories from our self-hosted GitHub Enterprise Server (GHES) to GitHub EU — a cloud-hosted GitHub instance with EU data residency, managed through Backstage. This is not a simple lift-and-shift. The two platforms are architecturally different and several capabilities we rely on today do not exist in cloud GitHub.

ACG (Automated Code Governance) is our internal CLI that writes and audits standard governance files across all repositories. It is wired into Backstage so new repos are governed from first commit with no manual steps.

We work in a regulated UK bank. FCA/PRA obligations, DORA operational resilience requirements, and internal data classification policies shape every decision here. A choice that would be straightforward elsewhere may require a formal CAB change request, business owner sign-off, and audit evidence in our context.

The three things this document answers

1. What do we have on GHES, and does it transfer to GitHub EU?

2. Where it does not transfer — what is the alternative and have we agreed it?

3. How do we execute the migration across ~250 repos without disrupting teams?

## 1.1 Current Platform: GHES

- Self-hosted — full server-level control including server-side hooks

- Pre-receive hooks — server-side hard block before a push is accepted (data upload prevention)

- Cloud Build for CI/CD — we do not use GitHub Actions on GHES; Cloud Build is triggered by GitHub webhook events

- GitHub Pages — accessible to all engineers without special access

- Full admin API access for automation and inventory

## 1.2 Target Platform: GitHub EU

- Cloud-hosted — org and repo level configuration only; no server access

- No pre-receive hooks — GHES-only feature; does not exist on GitHub.com/EU

- Cloud Build integration method changes — webhook becomes GitHub App (needs PoC confirmation)

- Backstage as the central portal for repo creation, catalog, governance, and documentation

- ACG as the automated governance layer replacing manual per-repo configuration

- GitHub Rulesets + required CI status checks as the merge-gate enforcement mechanism

| Today (GHES) — problems we are solving | After Migration (GitHub EU) — target state |
| --- | --- |
| Repos created manually with no standard | All repos created from Backstage templates |
| No enforced policy on what gets committed | ACG enforces governance on every repo |
| Pre-receive hooks prevent data uploads server-side | Rulesets + required CI checks at merge-gate |
| Cloud Build triggered via GHES webhooks | Cloud Build via GitHub App (needs PoC) |
| GitHub Pages open to all engineers | Docs in Confluence (interim) or Backstage (long-term) |
| Config differs per repo, per team | ACG standardises all repos automatically |
| No central catalog of what repos we own | Backstage catalog — single source of truth |
| No drift detection | Weekly ACG audit with Grafana dashboard |

# 2. The Urgent Open Question — Cloud Build on GitHub EU

⚠ Resolve before any D2 team gets a confirmed migration date

On GHES: Cloud Build is triggered by GitHub webhook events (push / pull_request).

On GitHub EU: Cloud Build connects via a GitHub App, not a webhook. Different mechanism.

Until this is tested and confirmed, D2 team migration dates are provisional.

## 2.1 The Technical Difference

|  | GHES (today) | GitHub EU (target) | Risk |
| --- | --- | --- | --- |
| Connection | Webhook — GHES sends events to Cloud Build trigger URL | GitHub App — Cloud Build app installed on GitHub EU org via OAuth | Different setup. Not just a URL change — new credentials and trigger config required. |
| Authentication | Webhook secret | GitHub App credentials (App ID + private key) | New credentials to create and manage. Platform team must approve App installation. |
| Status reporting | GitHub API via PAT or service account | GitHub App token (preferred on cloud GitHub) | PAT may not work the same way. Must test on GitHub EU. |
| Network path | Cloud Build → GHES (may be internal/private) | Cloud Build → api.github.com (public internet, EU-scoped) | If GHES is on private network: no issue today. GitHub EU requires egress to api.github.com. Security team must approve. |
| Trigger config | Cloud Build trigger references GHES repo URL | Trigger must reference GitHub EU repo URL | Triggers need recreating per repo, not just updating. |

## 2.2 Questions to Answer and Who to Ask

| Question | Ask Who |
| --- | --- |
| Has Cloud Build been tested with GitHub EU? Is there a confirmed integration approach? | Platform team + Cloud/GCP team |
| Is Cloud Build connecting to GHES via webhook or via the Cloud Build GitHub App? | Cloud/GCP team or whoever manages Cloud Build triggers |
| Are Cloud Build pipelines configured to report status back as required checks on PRs? | Each team with a Cloud Build pipeline |
| Does Cloud Build have approved egress to reach api.github.com from our environment? | Security/Network team + Cloud/GCP team |
| Will the platform team approve the Cloud Build GitHub App installation on GitHub EU org? | Platform team |
| What happens to existing Cloud Build triggers that reference GHES repo URLs after migration? | Cloud/GCP team |

Required: Run a Cloud Build PoC in Phase 0

Pick one non-critical repo with a Cloud Build pipeline. Work with platform team and Cloud/GCP team.

Set up Cloud Build GitHub App on GitHub EU org. Migrate that repo. Confirm trigger fires. Confirm status reporting works.

Document the setup steps — this becomes the template for all D2 team migrations.

Do this before Phase 1 ends. No D2 team gets a confirmed migration date without a successful PoC.

# 3. Feature Gap Analysis — GHES vs GitHub EU

| Status | Meaning |
| --- | --- |
| Open | Gap with no agreed alternative — needs a decision |
| Alternative | Clear alternative identified |
| In Progress | Being investigated |
| Resolved | Transfers directly or equivalent confirmed |
| TBC | Not yet assessed |

| Feature | GHES | GitHub EU | Gap / Alternative / Notes |
| --- | --- | --- | --- |
| SERVER-SIDE HOOKS |  |  |  |
| Pre-receive hooks | Available — data upload prevention | Not available | MAJOR GAP. Server-side hard block before push accepted. Enforcement moves from push-gate to merge-gate on GitHub EU. Replacement: CI required status checks + GitHub Rulesets. See Section 7 for the full replacement design. |
| Post-receive hooks | Available | Not as hooks | Alternative: GitHub Actions on push event. Equivalent for notifications and downstream triggers. |
| CI / BUILD |  |  |  |
| Cloud Build integration | Webhook-triggered from GHES | GitHub App (TBC — PoC required) | OPEN QUESTION. Integration mechanism changes from webhook to GitHub App. PoC required in Phase 0. No D2 migration dates without successful PoC. Cloud Build triggers need recreating per repo. Status reporting must be tested. Security approval needed for egress to api.github.com. |
| GitHub Actions | Not used on GHES | Available | New capability on GitHub EU. ACG governance workflow runs as a GitHub Actions workflow. Reusable workflow pattern is the enforcement mechanism. |
| Required status checks + Rulesets | Available | Available + org-level Rulesets | Improved. Rulesets provide org-level enforcement without per-repo config. Primary pre-receive hook replacement at merge-gate. |
| DOCUMENTATION |  |  |  |
| GitHub Pages | All engineers can view | Backstage access-restricted | SIGNIFICANT GAP. TechDocs in Backstage requires Backstage access. Currently only admins and owners have access. Most engineers cannot read governance docs. Interim: Confluence. Long-term: broader Backstage read access. See Decision 2. |
| REPOSITORY MANAGEMENT |  |  |  |
| Repo creation | GitHub UI or API | Backstage templates only | Process changes. All new repos via Backstage templates. Ensures consistent governed starting state. Teams using API scripts need to update their process. |
| Repo settings / config | Manual per-repo | ACG-managed | Improvement. ACG standardises settings across all repos, eliminating configuration drift. |
| Git history, branches, tags | Full | Full via GH Importer | Transfers using GitHub Enterprise Importer. Verify commit, branch, and tag counts post-migration. |
| Open PRs and Issues | Available | Migrated by importer | Transfers. GHES URLs in comments become stale but functional while GHES is read-only. |
| CODEOWNERS | Available | Available | Transfers directly with repo history. No action needed. |
| INTEGRATIONS & WEBHOOKS |  |  |  |
| Webhooks | Available | Available — URLs change | Webhook URLs change after migration. External systems stop receiving events. Inventory all webhooks. Update configs on migration day. |
| GitHub Apps / OAuth Apps | Available | Needs re-installation | Apps do not transfer. Re-install on GitHub EU org. Check EU data residency and cloud compatibility. Platform team must approve each. |
| Deploy keys / SSH keys | Available | Not transferred | Must be recreated per repo on GitHub EU. Inventory in discovery. Plan recreation as part of migration day steps. |
| GitHub Packages / Registry | Available (GHES registry) | Different namespace | Namespace changes. Pipelines and scripts referencing GHES registry will break. Re-publish packages to GitHub EU registry. Coordinate with consuming teams. |
| ACCESS & SECURITY |  |  |  |
| SSO / SAML | Self-managed | Org-level SAML | Supported. Confirm SAML configuration is in place for GitHub EU org before engineers are onboarded. |
| Secrets | GitHub Secrets | Available — not transferred | Encrypted to GHES instance. Every secret must be manually recreated on GitHub EU. Consider migrating to a central secrets manager. |
| Team permissions | GHES admin | Backstage-managed | Transfers but team membership needs re-mapping. Backstage manages team access to GitHub EU repos. |
| NEW CAPABILITIES (GitHub EU + ACG) |  |  |  |
| ACG — Automated Code Governance | N/A | New internal tooling | ACG writes and audits standard governance files across all repos. Wired into Backstage. New repos governed from first commit. Replaces manual per-repo configuration. |
| GitHub Rulesets (org-level) | N/A | New capability | Org-level push/merge rules applied across all repos without per-repo config. Key pre-receive hook replacement. |
| Backstage software catalog | N/A | New capability | Single view of all repos, ownership, and docs. ACG writes catalog-info.yaml. All migrated repos need this file added. |
| Drift detection | N/A | New via ACG | Weekly scheduled ACG audit feeds Grafana dashboard. Alerts on config drift, spec lag, enforcement mode. |

# 4. Open Design Decisions

Four decisions that must be made before the execution plan is finalised. All require platform team and/or leadership input.

## Decision 1 — Pre-Receive Hook Replacement

Required from: Engineering lead + Platform team

Pre-receive hooks gave a server-side hard block. GitHub EU has no equivalent.

Enforcement must move from push-gate to merge-gate. This needs explicit sign-off.

| Option | How It Works | Strength | Effort | Verdict |
| --- | --- | --- | --- | --- |
| GitHub Actions CI (required status check) | Runs on pull_request. Merge blocked if CI fails. | Strong merge-gate. Cannot block the push itself. | Low — reusable ACG workflow | Primary approach |
| GitHub Rulesets (file pattern rules) | Org-level rule blocks pushes of banned file types to default branch. | Partial push-gate for default branch. | Low — config only | Complement to CI |
| Custom GitHub App (push listener) | App receives push webhook, runs checks, reports as required check. | Closest to pre-receive. Very flexible. | High — custom build | Future option |

| Decision | Agreed? | Owner |
| --- | --- | --- |
| What replaces pre-receive hooks? | Pending | (fill) |
| Accept merge-gate vs push-gate enforcement? | Pending | (fill) |
| Which file types must be blocked? (from old hook scripts) | Pending | (fill) |

## Decision 2 — Engineer-Facing Documentation

Required from: Platform team + PM

TechDocs in Backstage is restricted to admins and owners. Most engineers — especially data scientists —

cannot read governance policy docs about rules being enforced on them.

| Option | Pros | Cons | Effort |
| --- | --- | --- | --- |
| Confluence (interim) | Most engineers have access. Immediately available. | Separate from code. | Low — start here |
| Broaden Backstage read access | Keeps docs next to the code. Long-term design. | Access policy change required. | Medium |
| GitHub Wiki (central repo) | No auth issues. | Less structured. | Low |

| Decision | Agreed? | Owner |
| --- | --- | --- |
| Where do engineer-facing docs live? | Pending | (fill) |
| Can we broaden Backstage read access? | Pending | (fill) |

## Decision 3 — Secrets Migration

Required from: Platform team + DevEx + team leads

Secrets are encrypted to the GHES instance. Every repo and org secret must be manually recreated.

| Decision | Options | Agreed? | Owner |
| --- | --- | --- | --- |
| How do we migrate secrets per repo? | Team self-service / DevEx coordinates / Central secret manager | Pending | (fill) |
| Move to a central secret manager? | Yes (Vault/AWS) / No — recreate in GitHub | Pending | (fill) |

## Decision 4 — GHES During and After Migration

| Decision | Options | Agreed? | Owner |
| --- | --- | --- | --- |
| GHES read-only for a repo immediately after it migrates? | Yes / 30-day window / Per tier | Pending | (fill) |
| How long does GHES stay accessible post full migration? | 30 / 60 / 90 days | Pending | (fill) |

# 5. What Transfers Cleanly

These items require no design decisions. They transfer with low or zero effort.

| Item | Notes |
| --- | --- |
| Git history, all branches, all tags | Migrated by GH Enterprise Importer. Verify: commit count, branch count, tag count. |
| Pull requests and issues | Migrated by GH Importer. GHES URLs become stale but functional during read-only period. |
| CODEOWNERS files | Text files — migrate with repo. No action needed. |
| GitHub workflow YAML files | Migrate with repo. ACG governance workflow added on top. Existing workflows unaffected. |
| README and in-repo markdown docs | Plain files — transfer with repo. |
| Branch protection config (per-repo) | Re-applied by ACG during governance setup. Improved with org-level Rulesets. |
| Labels and milestones | Migrated by GH Enterprise Importer. |
| Standard .gitignore | Transfers with repo. ACG standardises .gitignore going forward. |
| Repo visibility (public/private/internal) | Preserved on migration. Verify post-migration per repo. |

PART 2

Post-Migration Design

GitHub EU org structure, ACG steady state, data upload prevention, governance policy

# 6. Post-Migration Infrastructure Design

## 6.1 GitHub EU Org Structure

| Layer | Component | Description | Managed by |
| --- | --- | --- | --- |
| Organisation | github-eu-org | Single GitHub EU org containing all ~250 repos. SAML SSO enforced. | Platform team |
| Org-level | Rulesets | Org-wide push/merge rules: block banned file types, require PR, disallow force push. | Platform team |
| Org-level | org/governance repo | Central repo: reusable ACG CI workflow, versioned spec templates (spec/v1.x/), CHANGELOG. | Platform team |
| Org-level | github-acg-bot service account | Service account with write access to all repos. Used by ACG to open governance PRs. | Platform team |
| Team-level | Backstage teams | Each team has a Backstage team. Membership controls GitHub EU repo access. | Platform team + team leads |
| Repo-level | Branch protection | governance-ci required check. PR review required. No force push. Applied by ACG. | ACG (automated) |
| Repo-level | catalog-info.yaml | Backstage catalog entry per repo. Owner, lifecycle, spec version. Written by ACG. | ACG + repo team |

## 6.2 Backstage Architecture (Steady State)

| Component | Role | Who Uses It |
| --- | --- | --- |
| Software Catalog | Source of truth for all repos, owners, and metadata. Feeds from catalog-info.yaml. | All engineers (read) · Platform team (admin) |
| Templates | Standard repo creation. Engineers select template. ACG runs automatically. Governed from first commit. | All engineers |
| TechDocs | Governance policy docs and engineering guides. Currently admin/owner only. Interim: Confluence. | All engineers (read) · DevEx (write) |
| Scaffolder | Runs on template use. Calls ACG apply. Sets branch protection. Adds to catalog. All automated. | Automated |

## 6.3 ACG in Steady State

### Apply — new repo creation

- Called automatically by Backstage scaffolder when a new repo is created

- Writes: .gitignore, .github/workflows/governance.yml, catalog-info.yaml, mkdocs.yml

- Applies branch protection: governance-ci required, PR review required, no force push

- New repo is governed from its first commit. Zero manual steps.

### Audit — weekly drift detection

- Weekly scheduled GitHub Actions job in org/governance runs ACG audit --all

- Checks every repo: governance files present? Match current spec? Branch protection correct?

- Repos with drift: GitHub issue opened automatically

- If drift count > threshold: Slack alert to platform team on-call

- Feeds Grafana dashboard: coverage %, drift count, spec lag, false positives, enforcement mode

### Batch — migration and spec upgrades

- ACG apply --repo-list wave-N.txt runs governance across all repos in a wave file

- Produces machine-readable JSON log per repo: status, spec version, files written, PR URL, errors

- Used during migration waves and when governance spec is upgraded

## 6.4 Day-to-Day: Raising a PR

| Step | Normal Flow | If Something Fails |
| --- | --- | --- |
| Engineer pushes branch | Branch created. Org Ruleset: no banned file types pushed to default branch. | Push rejected if file type blocked by Ruleset. Clear error message. |
| PR opened | PR created targeting default branch. | N/A |
| governance-ci check runs | ACG reusable workflow runs: data file check, notebook output check, governance file check. | PR cannot merge. CI shows which check failed. Links to docs. |
| Code review | At least 1 approval required. | PR cannot merge without approval. |
| Merge | All required checks green. | Merge button disabled if any required check fails. |

## 6.5 Monitoring — Grafana Metrics

| Metric | What It Measures | Alert Threshold |
| --- | --- | --- |
| governance.coverage_pct | % of catalog repos with governance at current spec | < 95% → alert |
| governance.drift_count | Repos with governance files missing or modified | &gt; 5 → alert |
| governance.spec_lag_count | Repos more than 1 minor version behind spec | &gt; 20 → alert |
| governance.violations_per_week | PRs blocked by governance-ci | Informational |
| governance.false_positives_per_week | Violations reported as false positives | &gt; 3/week → review |
| governance.time_to_governed | Minutes from Backstage creation to governance applied | &gt; 15 min → alert |
| governance.enforcement_mode | Count of repos in warn vs. block mode | All block after migration |

# 7. Data Upload Prevention Design

On GHES, pre-receive hooks gave a server-side hard block before data files could enter a repo. On GitHub EU this mechanism does not exist. The replacement is layered: Rulesets block at push level for pattern-matched file types; CI blocks at merge level with content-aware checking.

## 7.1 What the Old Hook Was Protecting Against

| Risk | Why It Matters in a Bank |
| --- | --- |
| PII / customer data committed to git — e.g. a CSV containing account numbers or transaction history | Regulatory breach. Data in git history is permanent. Even a deleted file leaves traces. |
| Large data files bloating repos — e.g. a 50GB model training dataset committed to git | Storage cost, performance degradation, and poor data engineering practice. |
| Model weights and outputs — serialised model files (.pkl, .h5) alongside code | Model files can contain embedded training data. Storage and versioning problem. |
| Sensitive config / secrets accidentally committed | Security incident. Server-side enforcement was the guarantee. |

## 7.2 The Replacement Architecture — Three Layers

### Layer 1: GitHub Org Rulesets — Push Gate (partial)

| Rule | What It Does | Limitation |
| --- | --- | --- |
| Block push of specific extensions to default branch | Prevent .csv, .parquet, .pkl, .npy, .h5, .hdf5, .db, .sqlite, .zip, .tar, .gz, .7z from pushing directly to main | Only protects default branch. Feature branches unprotected. |
| Require PR before merging to default branch | No direct pushes to main. All changes go through a PR. | Does not check file content. Extension matching only. |

### Layer 2: ACG CI Governance Check — Merge Gate (primary)

The governance-ci required status check runs on every PR. A PR cannot merge if this fails.

| Guard | What It Checks | Result if Failed |
| --- | --- | --- |
| data-file-guard | File type matches blocked extension list. Size exceeds threshold inside tests/data/. | PR cannot merge. Clear error message. Exception process linked. |
| notebook-output-guard | Any .ipynb in the PR diff contains cell outputs or execution counts. | PR cannot merge. Instructions to strip outputs. nbstripout docs linked. |
| governance-file-guard | Required governance files present and match current spec version. | PR cannot merge. ACG governance PR must be merged first. |
| large-file-guard | Any single file in the PR diff exceeds size threshold (default: 10MB). | PR cannot merge. File must be removed from the PR. |

### Layer 3: Exception Process

- Engineer submits exception request via Backstage governance exception form

- Platform team reviews within 3 business days (urgent: same day via #github-migration)

- If approved: exception written into catalog-info.yaml under governance/exceptions

- ACG apply and audit respect declared exceptions

- Exceptions reviewed quarterly. Expired exceptions removed automatically.

## 7.3 What the Replacement Covers vs What It Does Not

| ✔ What is covered | ⚠ What it does not cover vs pre-receive |
| --- | --- |
| Banned file types blocked from merging to main (CI) | Cannot block push to feature branches — files can briefly exist |
| Banned types blocked from pushing to main directly (Ruleset) | Cannot scan file content (PII patterns, credentials) — extension and size only |
| Notebook outputs blocked from merging | No real-time block on the push itself — enforcement is at merge-gate |
| Large files blocked from merging | Content scanning (regex patterns for account numbers etc.) needs a separate tool |
| Governance file presence enforced on every PR | Consider adding Gitleaks or Trivy as an additional secrets scanning layer |
| Weekly drift detection catches bypass attempts |  |
| All CI failures logged in GitHub audit log |  |
| Exception process provides documented overrides for legitimate cases |  |

Important: If the old pre-receive hook scanned content patterns (PII, account numbers), that needs a separate design

Rulesets and CI file-type guards check extensions and sizes — not content.

If the old hook was checking for patterns (account number formats, credit card numbers, etc.):

that capability needs to be replaced by a dedicated secrets/content scanning tool.

Raise this with the platform team as a separate security requirement.

# 8. Governance Policy

Sign-off required from Engineering VP, Security lead, and major product team leads before Phase 3 bulk migration

Hard gate. Phase 3 does not start without written sign-off from all three parties.

## 8.1 Notebook Policy

| Rule | Detail |
| --- | --- |
| .ipynb files | Permitted in any directory. Notebooks themselves are not blocked. |
| Cell outputs | FORBIDDEN in any committed notebook. |
| Execution counts | FORBIDDEN in any committed notebook. |
| Enforcement | CI governance-ci check fails on any PR adding/modifying a .ipynb with outputs. |
| Exception | None. Outputs must always be stripped. Use nbstripout or equivalent. |

## 8.2 Data File Policy

| Rule | Detail |
| --- | --- |
| Blocked file types | .csv .tsv .parquet .feather .orc .pkl .pickle .npy .npz .h5 .hdf5 .db .sqlite .sqlite3 .zip .tar .tar.gz .tgz .gz .7z .rar |
| Allowed path | tests/data/** only — small test fixtures |
| Allowed size | ≤ 1 MB per file in tests/data/ |
| Enforcement | CI fails on any PR adding a banned file outside tests/data/, or exceeding size cap inside tests/data/ |
| Exception process | Submit via Backstage exception form. Platform team reviews within 3 business days. |

PART 3

Migration Execution Plan

Phases 0–4, master timeline, wave runbooks, validation checklists, rollback

# 9. Migration Execution Plan

Core principles

1. Inventory before touching anything — know what you have before you move it.

2. Policy signed off before enforcement — governance rules need stakeholder agreement.

3. Cloud Build PoC before D2 migrations — no D2 team gets a confirmed date without a successful PoC.

4. Pilot before bulk — validate on a small cohort before touching 250 repos.

5. Warn before block — CI starts in warn mode. Teams have a 5-day window before enforcement.

6. Wave-gated — do not start the next wave until the current one passes all exit criteria.

7. GHES stays read-only — never decommission until access logs confirm no active usage.

## 9.1 Master Timeline

| Period | Phase / Activity | Key Deliverable | Gate? |
| --- | --- | --- | --- |
| Wks 1–2 | Phase 0 — Foundation & Inventory | Repo inventory, tier classification, policy sign-off, GitHub EU org setup, ACG validated, Cloud Build PoC started | Yes — all success criteria |
| Wks 2–4 | Phase 1 — Backstage & ACG Integration | ACG wired into Backstage, governance spec v1.0, docs published, smoke test passed | Yes — all success criteria |
| Wks 4–6 | Phase 2 — Pilot Migration (10–20 repos) | Pilot repos migrated and governed in block mode, retrospective held | Yes — all success criteria |
| Wks 6–7 | Wave 1 — D1 Inactive | Low-risk inactive repos migrated. | Wave gate |
| Wks 7–8 | Wave 2 — D1 Active DS teams | Active data science repos. Governance impact first felt. | Wave gate |
| Wks 8–9 | Wave 3 — D1 Standard active | Bulk of simpler repos. | Wave gate |
| Wks 9–10 | Wave 4 — D1 Remaining | Complete D1 estate. | Wave gate |
| Wks 10–12 | Wave 5 — D2 Cloud Build integrated | ONLY after Cloud Build PoC confirmed. Triggers recreated and tested. | Wave gate + PoC |
| Wks 12–13 | Wave 6 — D3 Release / Package publishing | All downstream consumers mapped. Coordinated cutover. | Wave gate + consumer map |
| Wks 13–14 | Wave 7 — D4 Mission critical | Individual plans per repo. CAB approvals. Dedicated change windows. | Per-repo CAB approval |
| Wks 14–16 | Phase 4 — Hardening & Steady State | Coverage audit, drift detection live, Grafana dashboard, GHES read-only | Definition of Done |
| Wk 16+ | Ongoing — Steady State | Weekly drift, monthly metrics, GHES decommission at day 90 | Day 90 sign-off |

# 10. Phase Details

## Phase 0 — Foundation & Inventory (Weeks 1–2)

#### Repo Inventory — pull from GHES admin API and enrich each repo:

| Field | How to Get It |
| --- | --- |
| Primary language | GHES API GET /repos/:owner/:repo/languages |
| Last commit date | GHES API → pushed_at |
| Active contributors (12 months) | GHES API /contributors |
| Contains .ipynb files | GHES code search: extension:ipynb |
| Notebook output violations | nbstripout --verify on each .ipynb found |
| Contains banned data file types | GHES code search per blocked extension |
| Large files committed | git ls-files --others + size check |
| Cloud Build triggers on this repo | Cloud Build API — list triggers, filter by repo URL |
| Webhooks configured | GHES API GET /repos/:owner/:repo/hooks |
| GitHub Apps installed | GHES API → installed apps |
| Deploy keys | GHES API GET /repos/:owner/:repo/keys |
| Secrets (count only) | GHES API GET /repos/:owner/:repo/actions/secrets |
| GitHub Packages published | GHES API → packages |
| Team / BU ownership | Cross-reference CODEOWNERS or Backstage catalog |

#### Repo Dependency Tier Classification

| Tier | Criteria | Wave |
| --- | --- | --- |
| D1 — Code Store / Data Science | No Cloud Build triggers. No webhooks. Uses GitHub for code storage and notebooks only. | Waves 1–4 |
| D2 — Cloud Build Integrated | Has Cloud Build triggers. Pipeline fires on push/PR. May report required status checks. | Wave 5 (after PoC) |
| D3 — Release / Package Publishing | Publishes GitHub Packages or Releases consumed by other teams. | Wave 6 |
| D4 — Mission Critical | Prod deployment pipeline, regulatory control (four-eyes), or risk model feed. | Wave 7 |

#### Phase 0 Success Criteria

| Criterion | Done? |
| --- | --- |
| Inventory spreadsheet complete — every repo has a dependency tier and violation flags |  |
| Governance policy document signed off by Engineering VP, Security lead, and product team leads |  |
| GitHub EU org infrastructure operational (SAML, Rulesets, org/governance, ACG service account) |  |
| ACG CLI validated on 5 test repos (apply, audit, batch, idempotency confirmed) |  |
| Cloud Build PoC started (or completed if fast) |  |
| All four Open Design Decisions from Section 4 resolved |  |
| Backstage catalog contains all GHES repos (or reconciled inventory) |  |

## Phase 1 — Backstage & ACG Integration (Weeks 2–4)

#### Governance Spec v1.0 — what ACG writes to every repo

| File | What ACG Writes |
| --- | --- |
| .gitignore | Banned file extensions, Jupyter checkpoint dirs, Python artifact dirs |
| .github/workflows/governance.yml | Calls org/governance reusable workflow. mode: warn initially. Runs on pull_request. |
| catalog-info.yaml | apiVersion, kind, metadata (name, annotations incl. governance/spec-version: 1.0), spec (owner, lifecycle, type) |
| mkdocs.yml | Standard MkDocs config for TechDocs pipeline |

#### Phase 1 Success Criteria

| Criterion | Done? |
| --- | --- |
| Governance spec v1.0 defined and version-tagged in org/governance |  |
| Reusable governance CI workflow live in org/governance |  |
| Backstage scaffolder action live and tested on 3 net-new repos |  |
| Cloud Build PoC complete — integration approach confirmed |  |
| Governance docs published in agreed platform (Confluence or Backstage) |  |
| All Backstage repo templates updated to call ACG apply on creation |  |

## Phase 2 — Pilot Migration (Weeks 4–6)

#### Pilot cohort: 10–20 repos

| Category | Count | Purpose |
| --- | --- | --- |
| D1 inactive | 3–4 | Validate tooling with minimal risk |
| D1 active DS — no violations | 4–6 | Validate governance under normal conditions. Governance PR impact on DS teams. |
| D1 active DS — with notebook outputs in history | 2–3 | Validate warn-mode and legacy violation guidance. |
| D2 Cloud Build (one only, after PoC complete) | 0–1 | Early signal on Cloud Build migration. |

#### Per-repo migration steps

| Step | Timing | Detail |
| --- | --- | --- |
| Notify owner | T−7 days | Slack + email. What is happening, what changes, docs link, DevEx contact. |
| Dry run | T−2 days | ACG apply --dry-run <repo>. Review diff with owner. Move surprises to next wave. |
| Import | T+0 | Run GH Enterprise Importer. Poll until status = complete. |
| Verify import | T+0 | Commit count, branch count, tag count match GHES. |
| Apply governance | T+0 | ACG apply <repo>. Governance PR opened by github-acg-bot. |
| Set read-only on GHES | T+0 | GHES repo set to read-only. Log outcome to pilot-results.json. |
| Merge window | T+1 to T+5 | CI in warn mode. Owner reviews governance PR. DevEx merges at T+5 if no activity. |
| Enforcement cutover | T+5 | mode: warn → mode: block. Slack notification sent to team. |

#### Per-repo validation checklist

| Check | Pass? |
| --- | --- |
| All governance files present and correct |  |
| governance-ci check active on default branch |  |
| Clean PR → CI passes |  |
| PR with banned data file → CI fails with clear message |  |
| PR with notebook outputs → CI fails with clear message |  |
| No existing workflows broken |  |
| Repo in Backstage catalog correctly |  |
| GHES repo set to read-only |  |
| Cloud Build pipeline still fires correctly (D2 repos only) |  |

## Phase 3 — Bulk Migration Wave Runbook

#### Wave gate criteria — must all be met before starting the next wave

Do NOT start the next wave until ALL of the following are met

≥ 95% of governance PRs merged (not just opened)

Zero unresolved P0 issues (CI completely broken, team blocked on shipping)

False positive rate < 5% for the wave

< 2% repos with 'failed' import status in machine-readable log

Wave metrics reviewed by you and platform team lead — sign-off given

#### Wave execution timeline (per wave)

| Step | Timing | Detail |
| --- | --- | --- |
| Prepare wave repo list | T−14 days | Create wave-N.txt with org/repo per line. Grouped by team. |
| Send team notifications | T−7 days | Slack + email to each affected team channel. Use template in Section 19. |
| Run dry run | T−2 days | ACG apply --dry-run --repo-list wave-N.txt > wave-N-dryrun.json |
| Review dry run output | T−2 days | Large unexpected diffs → move to next wave. Unresolvable conflicts → Wave 7. |
| Migration day — import | T+0 | Run GH Enterprise Importer per repo. Parallelise per team, not all at once. |
| Migration day — verify | T+0 | Commit, branch, tag counts match between GHES and GitHub EU. |
| Migration day — govern | T+0 | ACG apply --repo-list wave-N.txt. Governance PRs opened by github-acg-bot. |
| Migration day — GHES read-only | T+0 | Set GHES repos to read-only. Log outcome to wave-N-results.json. |
| Merge window | T+1 to T+5 | CI in warn mode. Monitor PR merge rate daily. Respond to false positives same day. |
| Auto-merge unmerged PRs | T+5 | DevEx merges any governance PRs with no activity. Pre-communicated at T−7. |
| Enforcement cutover | T+5 | Single commit to org/governance: mode: warn → mode: block. Slack notification sent. |
| Wave close review | T+7 | Review wave-N-results.json. Stats, patterns, false positives. Platform team signs off. |

## Phase 4 — Hardening & Steady State (Weeks 14–16+)

- Run ACG audit --all --format json > coverage-audit.json. Remediate all gaps.

- Confirm weekly drift detection job is live in org/governance and alerting correctly.

- Confirm Grafana dashboard showing all 7 metrics from Section 6.5.

- GHES decommission: read-only for agreed window (30/60/90 days). Decommission at day 90 with platform team sign-off.

## Rollback Procedures

### Single repo — target: < 30 minutes

- Click 'Revert' on the governance PR in GitHub EU. Repo becomes ungoverned.

- Platform team / DevEx diagnoses root cause.

- Fix in org/governance central workflow, or add exception to catalog-info.yaml.

- Re-open governance PR. Repo goes back through the 5-day merge window.

### Wave-level — target: < 2 hours

- Platform team lead halts the wave immediately.

- Single commit to org/governance: mode: warn for all wave repos. Propagates immediately.

- Repos stop blocking PRs within minutes. No per-repo action required.

- Incident review within 24 hours. Fix root cause. Re-run dry run before restarting.

PART 4

Team Engagement

Dependency tiers, data science teams, platform team relationship

# 11. Team Dependency Tiers

Classify every team into one dependency tier. This determines wave order and engagement intensity. Use the highest applicable tier.

D1 — Code Store / Data Science ¦ Majority of your estate ¦ LOW risk

Teams using GitHub as a remote store for notebooks, scripts, and analysis code. No automated pipelines, no external integrations, no publishing. This is the majority of your data science estate. Signs: · No Cloud Build triggers on these repos · No webhooks configured · Jupyter notebooks committed (often with outputs) · Data files sometimes present in the repo · Commits infrequent or exploratory Risk: LOW · Engineers will notice the URL has changed. That is the main disruption. · The governance PR will appear — may confuse data scientists unfamiliar with the process. · Notebook output and data file rules have the biggest impact on this group. · GHES set to read-only immediately after migration. Migrate: Waves 1–4 — migrate first, standard process

D2 — Cloud Build Integrated ¦ MEDIUM risk ¦ OPEN QUESTION pending PoC

Teams whose repos trigger Cloud Build pipelines on push or PR events. Could be model training, automated testing, or deployment automation. Integration mechanism changes on migration. Signs: · Cloud Build triggers reference this repo's URL · Push or PR events trigger a Cloud Build job · Cloud Build may report a required status check back to PRs · Team's workflow depends on Cloud Build completing Risk: MEDIUM — higher if Cloud Build → GitHub EU is not confirmed · Cloud Build triggers need recreating to point at GitHub EU repo URLs. · Platform team must approve Cloud Build GitHub App on GitHub EU org. · Status check reporting must be confirmed working before migration day. · Do NOT migrate any D2 team without a successful Cloud Build PoC first. Migrate: Wave 5 — ONLY after Cloud Build PoC is complete and confirmed

D3 — Release & Package Publishing ¦ HIGH risk ¦ Cross-team blast radius

Teams publishing Python packages, model artifacts, or GitHub Releases consumed by other teams. Migration changes the package namespace or release URL — downstream teams break. Signs: · GitHub Packages used to publish Python packages or Docker images · GitHub Releases tag versioned artifacts consumed by other teams · Other teams pip install or docker pull from this team's packages · Downstream consumers have references to the GHES registry Risk: HIGH — downstream teams affected, not just this team · GitHub Packages namespace changes. Downstream pip installs break. · Map ALL consumers before migration day. · Package re-publishing to GitHub EU registry happens on migration day, not before. · Coordinated cutover: publishing team and all consumers update references on the same day. Migrate: Wave 6 — only after all downstream consumers are mapped and ready

D4 — Mission Critical ¦ CRITICAL risk ¦ Formal change process required

Repos whose Cloud Build pipelines deploy to production, where PR approval is an auditable four-eyes control, or whose outputs feed regulatory or risk reporting systems. Disruption here is potentially a regulated operational resilience event under DORA and FCA requirements. Signs: · Cloud Build pipeline deploys to production or pre-production · PR approval is a segregation of duties / four-eyes control · Repo output feeds a risk model, regulatory report, or compliance system · Business owner exists outside the tech team · Migration failure could affect a reportable business service Risk: CRITICAL — potentially a regulated operational resilience event · Raise a formal CAB change request. Business owner must sign off. · Dedicated change window — agreed in writing, weekend morning preferred. · Repo freeze: no PRs, no releases, no Cloud Build deployments during migration window. · Platform team engineer present throughout migration day. Not just on standby. · 4-week hypercare period post-migration. Migrate: Wave 7 — last, individually planned, formal CAB change request required

# 12. Data Science Teams — Special Handling

## 12.1 How Data Scientists Use GitHub Differently

| Software engineers — GitHub is core workflow | Data scientists — GitHub is peripheral |
| --- | --- |
| Daily git users — branching, rebasing, PRs | Often use git minimally — push/pull, not much more |
| CI/CD central to their work | May commit directly to main |
| Comfortable reading CI failure messages | Less familiar with CI failure messages |
| Know how to update a git remote URL | Updating a git remote URL may need a guide |
| PRs are frequent and normal | PRs are less frequent |
| Configuration files are familiar | YAML governance files may look unfamiliar |

## 12.2 Controls That Hit Data Scientists Hardest

| Control | Impact | What to Prepare |
| --- | --- | --- |
| Notebook output stripping | HIGH. Sharing notebooks with outputs is a normal workflow. | Explain WHY (data protection, PII risk). Provide alternative: export as HTML/PDF for sharing. Show how nbstripout works. Have this ready BEFORE their migration date. |
| Data file blocking | HIGH. Committing CSVs and reference data is routine. Git history IS their data lineage. | Have an approved alternative confirmed BEFORE comms go out. Which GCS bucket or data platform should data live in? Do not communicate the block without the alternative. |
| Branch protection — PR required | MEDIUM. Teams committing directly to main need to change workflow. | Communicate early. Show that Backstage templates create repos with this already applied. |
| Required PR review | MEDIUM. Small DS teams may not have a code review culture for notebooks. | Platform standard — not negotiable. Acknowledge the change. Point to exception process. |

## 12.3 Where Data Should Live Instead of GitHub

Confirm these answers with platform team BEFORE communicating the data file policy to teams

Do not tell engineers what they cannot do without telling them what they should do instead.

| Use Case | Alternative | Who Confirms |
| --- | --- | --- |
| Reference datasets for analysis | Designated GCS bucket or internal data platform. Reference the path in the notebook. | Platform team + Data Engineering |
| Small test fixtures | Allowed in tests/data/ up to 1MB. Exception process for anything larger. | Platform team |
| Model weights and outputs | Model registry (MLflow, Vertex AI, or bank equivalent). Reference by run ID. | ML Platform team |
| Sharing notebook results | Export as HTML or PDF. Share via Confluence, SharePoint, or email. | Agree as team convention |
| Data versioning / lineage | DVC (Data Version Control) or document data version in notebook header. | Platform team to confirm approved tooling |

# 13. Platform Team Relationship — Working Within Their Guardrails

The platform team sets the standards. They define what ACG writes, what the governance spec contains, what Rulesets are applied, and what Backstage templates produce. You coordinate teams to work within those standards.

| Platform Team Owns | PM (You) Own |
| --- | --- |
| GitHub EU org configuration and standards | Migration project plan and timeline |
| ACG specification and governance spec | Team engagement and change management |
| Backstage templates and scaffolder | Repo inventory and dependency classification |
| GitHub EU org-level Rulesets | Wave scheduling and sequencing |
| Cloud Build → GitHub EU integration design | Tracking migration status per repo |
| Exception process approvals | Stakeholder reporting to your manager |
| Technical rollback execution | Running decisions through the exception process on behalf of teams |
| Approving GitHub App installations | D4 change requests and CAB coordination |

## 13.1 What You Need from Platform Team at Each Stage

| Phase | Specific Ask | When |
| --- | --- | --- |
| Discovery | Access to GitHub EU org for API queries. Walkthrough of ACG current state. | Immediately |
| Phase 0 — org setup | Set up org-level Rulesets. Create org/governance repo. Set up github-acg-bot service account. Confirm SAML. | Start Week 1 — complete by end Week 2 |
| Phase 0 — Cloud Build PoC | Run a Cloud Build → GitHub EU integration test on one non-critical repo. Document steps. | Start Week 1 — complete before D2 dates set |
| Phase 1 — Backstage templates | Update templates to call ACG apply on new repo creation. | 2-week lead time. Start Week 2 for Week 4 delivery |
| Phase 1 — docs platform | Agree where engineer-facing docs live. Configure access if Backstage. | Decision needed by end Week 3 |
| Pre-wave | Review wave repo list. Confirm Cloud Build readiness for D2 waves. Review dry-run concerns. | 2 weeks before each wave |
| D4 repos | Platform engineer attends 1:1 session with D4 repo owner. | 4 weeks before each D4 migration |
| Phase 4 | Set up drift detection job. Configure Grafana dashboard. Confirm alert routing. | Weeks 14–16 |

## 13.2 Meeting Cadence

| Meeting | Frequency | What You Prepare |
| --- | --- | --- |
| Standing migration sync | Fortnightly (weekly during active waves) | Wave status, open actions, next 2 weeks plan, specific asks for platform team |
| Wave planning session | 2 weeks before each wave | Wave repo list, team notification drafts, Cloud Build readiness confirmation for D2 waves |
| Cloud Build PoC review | Once — end of Phase 0 | Listen and capture the confirmed setup approach for D2 migration template |
| D4 repo deep-dive | Per D4 repo | Repo dependency map, draft change request, questions for platform team |
| Phase retrospective | End of each phase | Feedback from teams collected during the phase |

PART 5

Communication & Engagement Plans

What to say, when, to whom — and per-tier step-by-step engagement

# 14. Communication Plan

## 14.1 Communication Principles

- Tell teams before they ask. The worst outcome is an engineer discovering their repo moved without warning.

- For data scientists: plain English only. Do not reference .ipynb or nbstripout in a comms email.

- Always include the alternative. Do not tell engineers what is blocked without telling them what to do instead.

- Send to team Slack channel directly — not only to the team lead.

- Close the loop after enforcement activates — confirm it happened and what to do if a PR fails.

## 14.2 Communication Timeline

| Touchpoint | Channel | Message | Who |
| --- | --- | --- | --- |
| All-engineers announcement (Phase 0 complete) | Slack + email | We are migrating ~250 repos to GitHub EU over ~14 weeks. 7 days notice before your repos move. New governance controls including notebook and data file rules. Docs: [link] | You |
| DS team pre-briefing (before any DS wave) | Slack + Confluence doc | What the new notebook and data file rules mean for your workflow, and where data should live instead. | You + Platform team |
| T−30 days (D3 and D4 only) | 1:1 call | Starting the planning conversation. Walk through dependencies, change window, what they need to prepare. | You + Platform engineer |
| T−7 days (all teams) | Team Slack + email | See templates in Section 19 | You |
| T+0 governance PR comment | Automated PR comment | ACG explains each file added. States CI is in warn mode for 5 days. Links to docs. | ACG automated |
| T+5 enforcement notice | Team Slack | CI is now enforcing. Here is what a failing PR looks like and how to fix it: [link] | You |
| Wave close | Team Slack | Migration complete. GHES read-only. Any issues: #github-migration | You |
| Monthly steady state | #engineering-announce | Governance stats: violations caught, coverage %, any policy updates. | You or Platform lead |

# 15. Engagement Plans Per Tier

## 15.1 D1 — Code Store / Data Science

| Stage | Action | When |
| --- | --- | --- |
| Discovery | Flag as D1. Check for hidden Cloud Build triggers or webhooks. Note notebooks with outputs and data files. | Phase 0 |
| DS pre-brief | Send Confluence doc: notebook and data file rules, alternatives for data storage. Before their wave, not on migration day. | 3–4 weeks before |
| T−7 notification | Standard notification to team Slack. Data science version if DS team. See Section 19. | T−7 days |
| Migration day | Standard wave process. ACG apply runs. Governance PR opened. | T+0 |
| Governance PR nudge | If no activity after 2 days, one Slack reminder to team channel. | T+2 |
| Enforcement | CI switches to block. Slack confirmation. Link to failure guide. | T+5 |
| Follow-up | Monitor #github-migration for DS questions. Update FAQ from their questions. | Week 1 post-enforcement |

## 15.2 D2 — Cloud Build Integrated

| Stage | Action | When |
| --- | --- | --- |
| Discovery | Flag as D2. List all Cloud Build triggers. Confirm whether CI check is required on PRs. | Phase 0 |
| Cloud Build PoC | Track with platform team. Do not set migration dates until PoC is confirmed. | Phase 0/1 |
| D2 briefing call | 30-min call: Cloud Build change explained, what we are handling, what they need to do. | 3–4 weeks before (after PoC) |
| Trigger migration plan | Work with Cloud/GCP team to recreate Cloud Build triggers pointing at GitHub EU URLs. | 2 weeks before |
| Status check confirmation | Confirm Cloud Build status reporting works on GitHub EU from PoC results. | 2 weeks before |
| T−7 notification | Standard notification plus: Cloud Build pipelines have been updated. Please test post-migration. | T−7 days |
| Migration day | Migrate repo. Recreate trigger. Confirm trigger fires. Confirm status check reports correctly. | T+0 |
| Verify | Team lead confirms a real push triggered Cloud Build within 4 hours of migration. | T+0 same day |
| Enforcement | Standard T+5 enforcement. Confirm Cloud Build status check still passing. | T+5 |

## 15.3 D3 — Release & Package Publishing

| Stage | Action | When |
| --- | --- | --- |
| Discovery | Flag as D3. List all packages published. Map every team consuming these packages. | Phase 0 |
| Consumer mapping | Contact every consuming team. Tell them what changes and when. | 4–6 weeks before |
| Package migration plan | Agree with Cloud/GCP team how packages are re-published to GitHub EU registry. | 3–4 weeks before |
| Coordinated cutover | Agree date: publishing team and all consumers update references together. | 2–3 weeks before |
| T−7 notification | Send to publishing team AND all consuming teams. Explicit about what URL changes and when. | T−7 days |
| Migration day — coordinated | Migrate repo. Re-publish packages. Consumers update references. Confirm together. | T+0 (coordinated event) |
| Follow-up | Check consuming teams' pipelines and installs still work. 2-week check-in. | 2 weeks post-migration |

## 15.4 D4 — Mission Critical

| Stage | Action | When |
| --- | --- | --- |
| Discovery | Flag as D4. Document exactly why: prod deployment? regulatory control? risk model feed? | Phase 0 |
| Escalate to platform team | Bring to platform team lead. D4 repos need platform team active involvement. | Phase 0 |
| Business owner identification | Find the business owner outside the tech team. They must agree to the migration. | Phase 0 |
| Planning session | 90 min: you + platform engineer + tech lead + business owner. Map every dependency. | 4 weeks before |
| CAB change request | Raise formal change request. Attach this plan, rollback procedure, validation checklist. | 3–4 weeks before |
| Change window agreement | Specific time slot in writing from business owner. Weekend morning preferred. | 2 weeks before |
| Repo freeze | No PRs, no releases, no Cloud Build deployments during migration window. | T−2 days |
| Migration day | Dedicated session. Platform engineer present. You manage comms. Step-by-step validation. | T+0 (change window) |
| Post-migration validation | Full checklist. Email to business owner and change manager. Update CAB record. | T+0 same day |
| Hypercare | Daily check-in with tech lead. Any issue: same-day platform team response. | 4 weeks post-migration |

PART 6

Risks, Gaps & Definition of Done

Risk register, gaps tracker, and what 'complete' looks like

# 16. Risk Register

| Risk | Affects | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| Cloud Build does not work with GitHub EU as expected | D2 | Medium | High | Run PoC in Phase 0. Do not commit D2 dates without a successful PoC. Have fallback options ready (see Section 2). |
| Engineers commit data files before CI enforcement activates | D1 (DS) | High | Medium | 5-day warn window gives time to educate. Ensure alternative data storage is communicated before enforcement activates. |
| Data scientists panic when notebook CI fails | D1 (DS) | High | Medium | Pre-brief all DS teams before their migration. Confluence page with plain-English instructions. Same-day response to false positives. |
| Package consumers break when D3 repo migrates | D3 | Medium | High | Map all consumers before migration. Coordinated cutover on migration day. Do not migrate publishing team without consumer coordination. |
| Secrets missing post-migration causes pipeline failures | D2, D3, D4 | High | High | Inventory all secrets. Recreation is part of migration day steps. Confirm with team lead before sign-off. |
| Webhook URLs change and external tools stop receiving events | D2, D3, D4 | High | Medium | Inventory all webhooks. Update configs on migration day. Test webhook delivery post-migration. |
| D4 migration coincides with a production release | D4 | Medium | Critical | Repo freeze 2 days before. Agree change window explicitly. Business owner must approve. |
| Platform team capacity blocks wave execution | All | Medium | Medium | 2-week minimum lead time for all platform team asks. Escalate early if slipping. |
| CI false positives block legitimate work | All | Medium | High (D4) | CI starts in warn mode. 5-day window. False positives: same-day response. Rollback < 30 minutes. |
| Old pre-receive hook checked content patterns — replacement does not | All | TBC | High | Clarify with platform team and security what the old hook checked. Design content scanning solution separately if needed. |

# 17. Gaps Tracker

Living log. Review at every meeting with platform team.

| # | Gap | Impact | Status | Alternative / Action / Owner |
| --- | --- | --- | --- | --- |
| G01 | No pre-receive hooks on GitHub EU | High | Open | Decision 1. CI required checks + Rulesets recommended. Needs sign-off. Owner: (fill). |
| G02 | Cloud Build → GitHub EU integration unconfirmed | High | Open | Run PoC in Phase 0. No D2 migration dates until PoC complete. Owner: Platform team + Cloud/GCP. |
| G03 | TechDocs / GitHub Pages access restricted | High | Open | Decision 2. Interim: Confluence. Long-term: broaden Backstage access. Owner: (fill). |
| G04 | Secrets do not transfer | High | Open | Decision 3. Team self-service or central secret manager. Owner: (fill). |
| G05 | No confirmed alternative data storage for DS teams | High | Open | Platform + Data Engineering must confirm approved storage before comms go out. Owner: (fill). |
| G06 | Deploy keys do not transfer | Medium | In Progress | Recreate per repo as part of migration day steps. Inventory in discovery. Owner: DevEx. |
| G07 | Webhook URLs change on migration | Medium | In Progress | Update webhook configs in external systems on migration day. Inventory all webhooks. Owner: DevEx. |
| G08 | GitHub Packages namespace changes | High | TBC | Map all consuming teams. Re-publish to GitHub EU registry. Coordinated cutover. Owner: (fill). |
| G09 | GitHub Apps need re-installation | Medium | TBC | Inventory all installed apps. Check EU compatibility. Platform team must approve. Owner: (fill). |
| G10 | Content scanning (PII patterns) not in replacement design | High | Open | Clarify if old hook scanned content patterns. Design separate secrets scanning solution if so. Owner: (fill). |

# 18. Definition of Done

### Migration Complete

| Criterion | Done? |
| --- | --- |
| 100% of GHES repos migrated to GitHub EU with full history intact |  |
| 100% of migrated repos have ACG governance applied at current spec version |  |
| governance-ci is a required check on every repo's default branch |  |
| Zero repos in warn mode — all in block mode |  |
| All D4 repos either in standard or have an approved documented exception |  |

### Governance System Complete

| Criterion | Done? |
| --- | --- |
| Backstage scaffolder: new repos governed from first commit, zero manual steps |  |
| Weekly drift detection running and alerting |  |
| Grafana dashboard live with all 7 metrics |  |
| Exception process documented and first quarterly review completed |  |

### Infrastructure Complete

| Criterion | Done? |
| --- | --- |
| GHES accessible read-only; decommission date confirmed |  |
| github-acg-bot service account operational with correct scoped permissions |  |
| Cloud Build integration confirmed working on GitHub EU for all D2 repos |  |
| Rollback runbooks tested (at least one single-repo rollback dry-run) |  |

### Team Enablement Complete

| Criterion | Done? |
| --- | --- |
| Governance docs published and accessible to all engineers |  |
| Data science teams briefed on notebook and data file rules with confirmed alternatives |  |
| All teams received at least one wave notification |  |
| #github-migration Slack channel exists with documented response SLA |  |

PART 7

Templates

T−7 notifications, weekly status report, meeting log, decisions & actions log, team register

# 19. T−7 Notification Templates

## 19.1 Standard Version (D1 teams — non DS)

Subject: Your GitHub repos are moving to GitHub EU on [DATE]

Hi [Team Name],

Your repos are moving from GitHub Enterprise Server to GitHub EU on [DATE].

Repos: [list repo names]

What will happen:

· Full git history, open PRs, and issues migrate intact.

· A governance PR will be opened automatically. Please review and merge within 5 business days.

· CI checks will initially warn (not block). After you merge the governance PR, they will enforce.

· GHES becomes read-only for these repos for [X] days.

What you need to do:

· Update your local git remote after migration: git remote set-url origin [new-URL]

· Read the 2-minute governance guide: [Confluence link]

· No other action required.

Questions: #github-migration in Slack. Thanks, [Your name]

## 19.2 Data Science Version (D1 DS teams)

Subject: Your GitHub repos are moving to GitHub EU on [DATE] — important change for notebooks and data files

Hi [Team Name],

Your repos are moving to GitHub EU on [DATE]. Repos: [list]

What will happen:

· All your code, notebooks, and git history move intact. Nothing is lost.

· The GitHub URL for your repos changes. After migration, update your local git remote:

git remote set-url origin [new-URL]

· A governance PR will appear. Review and merge it within 5 business days.

New rules for notebooks (enforced after you merge the governance PR):

· Notebooks committed to GitHub must not have cell outputs or execution counts.

Initially CI will warn you. After the 5-day window it will block PRs with notebook outputs.

What to do: strip outputs before committing. How: [link to guide]

Why: committed outputs can contain sensitive data including customer information.

New rules for data files:

· Data files (CSV, pickle, parquet, etc.) cannot be committed to GitHub.

Where to put your data instead: [approved GCS bucket / internal data platform — fill this in]

Small test fixtures allowed in tests/data/ (under 1MB).

Need an exception? [Backstage exception form link]

· All changes to the main branch now require a PR (cannot push directly).

· At least one team member must approve your PR before it merges.

Full guide (5 mins, plain English): [Confluence link]

Questions: #github-migration in Slack. Thanks, [Your name]

## 19.3 Cloud Build Version (D2 teams)

Subject: Your GitHub repos are moving to GitHub EU on [DATE] — Cloud Build update included

Hi [Team Name],

Your repos are moving to GitHub EU on [DATE]. Repos: [list]

What will happen:

· Full git history, open PRs, and issues migrate intact.

· Your Cloud Build pipeline has been updated to point at GitHub EU. [Trigger names: list]

· A governance PR will be opened. Review and merge within 5 business days.

· GHES becomes read-only for these repos.

What you need to do:

· After migration day, run a test push or open a test PR to confirm your Cloud Build pipeline fires correctly.

· If Cloud Build does not trigger or status check does not report: post in #github-migration immediately.

· Update your local git remote: git remote set-url origin [new-URL]

Questions: #github-migration in Slack. Thanks, [Your name]

# 20. Weekly Status Report Template

Publish every Monday. Share with your manager.

| Field | Value |
| --- | --- |
| Report date | (fill — Monday date) |
| Reporting period | Week (fill) of 16 |
| Overall RAG | Green / Amber / Red |
| Current phase / wave | (fill) |
| Next milestone | (fill — what and when) |
| Prepared by | (your name) |

| Area | RAG | One-line summary |
| --- | --- | --- |
| Overall migration | Green / Amber / Red |  |
| Repo inventory | Green / Amber / Red |  |
| Cloud Build PoC | Green / Amber / Red |  |
| ACG tooling | Green / Amber / Red |  |
| Wave execution | Green / Amber / Red |  |
| Governance PR merge rate | Green / Amber / Red |  |
| Platform team dependencies | Green / Amber / Red |  |

| Metric | Value |
| --- | --- |
| Repos migrated this week | (fill) — total: (fill) / ~250 |
| Governance PRs merged | (fill) of (fill) opened |
| Repos in block mode | (fill) — % of migrated |
| False positives reported | (fill) — resolved: (fill) |
| Open P0 issues | (fill) |
| Cloud Build PoC status | Not started / In progress / Complete |

| Issue / Risk | Severity | Owner | Status | Action |
| --- | --- | --- | --- | --- |
| (fill) | High / Med / Low | (fill) | Open | (fill) |
| (fill) | High / Med / Low | (fill) | Open | (fill) |

| Decisions Needed from Manager / Platform Team | By When |
| --- | --- |
| (fill or None this week) | (fill) |

# 21. Meeting Log Template

| Field | Value |
| --- | --- |
| Meeting type | Kickoff / Platform team sync / Wave planning / D4 working session / Retrospective / Ad-hoc |
| Date & time | (fill) |
| Location / link | (fill) |
| Facilitator | (fill) |
| Note taker | (fill) |

| Name | Role / Team | Present? |
| --- | --- | --- |
| (fill) | (fill) | Yes / No / Apologies |
| (fill) | (fill) | Yes / No / Apologies |
| (fill) | (fill) | Yes / No / Apologies |
| (fill) | (fill) | Yes / No / Apologies |

| # | Agenda Item | Owner | Time |
| --- | --- | --- | --- |
| 1 | (fill) | (fill) | (fill) mins |
| 2 | (fill) | (fill) | (fill) mins |
| 3 | (fill) | (fill) | (fill) mins |
| 4 | Actions review | PM | 5 mins |

Notes: (fill per agenda item)

| # | Decision | Rationale | Decided By |
| --- | --- | --- | --- |
| 1 | (fill) | (fill) | (fill) |
| 2 | (fill) | (fill) | (fill) |

| # | Action | Owner | Due | Status |
| --- | --- | --- | --- | --- |
| 1 | (fill) | (fill) | (fill) | Open |
| 2 | (fill) | (fill) | (fill) | Open |
| 3 | (fill) | (fill) | (fill) | Open |

# 22. Decisions & Actions Log

## Decisions Log

| ID | Date | Decision | Decided By | Meeting Ref |
| --- | --- | --- | --- | --- |
| D001 | (fill) | Governance policy signed off | Eng VP + Security + Product leads | (fill) |
| D002 | (fill) | Pre-receive hook replacement agreed: CI + Rulesets | Platform team + Eng lead | (fill) |
| D003 | (fill) | Cloud Build PoC outcome and confirmed integration approach | Platform team + Cloud/GCP | (fill) |
| D004 | (fill) | Engineer-facing docs platform agreed | PM + Platform team | (fill) |
| D005 | (fill) | Secrets migration approach agreed | Eng lead + DevEx | (fill) |
| D006 | (fill) | GHES read-only window length confirmed | PM + Manager | (fill) |
| D007 | (fill) | Approved alternative data storage for DS teams confirmed | Platform + Data Eng | (fill) |
| D008 | (fill) | (fill) | (fill) | (fill) |

## Actions Log

| ID | Date | Action | Owner | Due | Status |
| --- | --- | --- | --- | --- | --- |
| A001 | (fill) | Inventory all repos from GHES admin API | DevEx | End Wk 1 | Open |
| A002 | (fill) | Start Cloud Build → GitHub EU PoC | Platform + Cloud/GCP | End Wk 2 | Open |
| A003 | (fill) | Get written policy sign-off from Eng VP and Security | PM | End Wk 2 | Open |
| A004 | (fill) | Confirm approved alternative data storage for DS teams | Platform + Data Eng | End Wk 2 | Open |
| A005 | (fill) | Create org/governance repo in GitHub EU with reusable workflow | DevEx | End Wk 3 | Open |
| A006 | (fill) | Publish governance docs in agreed platform | DevEx + PM | End Wk 4 | Open |
| A007 | (fill) | Classify all repos into dependency tier (D1–D4) | DevEx | End Wk 2 | Open |
| A008 | (fill) | Identify pilot cohort (10–20 repos) with owner agreement | DevEx + PM | End Wk 3 | Open |
| A009 | (fill) | Send Wave 1 T−7 notifications to affected teams | PM | (T-7 date) | Open |
| A010 | (fill) | (fill) | (fill) | (fill) | Open |

# 23. Team Register — Working Tracker

One row per team. Fill during discovery phase.

Column guide

Dep. Tier: D1 (code store / DS) / D2 (Cloud Build) / D3 (release/packages) / D4 (mission critical)

DS Team: Yes / No Cloud Build: Yes / No / TBC

Notebooks w/outputs: Yes / No Data files: Yes / No (found during inventory)

Status: Pending / Briefed / Notified / Dry Run / Migrated / Governed / Complete

| Team Name | Team Lead | Slack | Dep. Tier | DS? | Cloud Build? | Wave | Mig. Date | Status | Notes / Flags |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| (fill) | (fill) | #(fill) | D1/2/3/4 | Y/N | Y/N/TBC | (fill) | (fill) | Pending |  |
| (fill) | (fill) | #(fill) | D1/2/3/4 | Y/N | Y/N/TBC | (fill) | (fill) | Pending |  |
| (fill) | (fill) | #(fill) | D1/2/3/4 | Y/N | Y/N/TBC | (fill) | (fill) | Pending |  |
| (fill) | (fill) | #(fill) | D1/2/3/4 | Y/N | Y/N/TBC | (fill) | (fill) | Pending |  |
| (fill) | (fill) | #(fill) | D1/2/3/4 | Y/N | Y/N/TBC | (fill) | (fill) | Pending |  |
| (fill) | (fill) | #(fill) | D1/2/3/4 | Y/N | Y/N/TBC | (fill) | (fill) | Pending |  |
| (fill) | (fill) | #(fill) | D1/2/3/4 | Y/N | Y/N/TBC | (fill) | (fill) | Pending |  |
| (fill) | (fill) | #(fill) | D1/2/3/4 | Y/N | Y/N/TBC | (fill) | (fill) | Pending |  |
| (fill) | (fill) | #(fill) | D1/2/3/4 | Y/N | Y/N/TBC | (fill) | (fill) | Pending |  |
| (fill) | (fill) | #(fill) | D1/2/3/4 | Y/N | Y/N/TBC | (fill) | (fill) | Pending |  |
| (fill) | (fill) | #(fill) | D1/2/3/4 | Y/N | Y/N/TBC | (fill) | (fill) | Pending |  |
| (fill) | (fill) | #(fill) | D1/2/3/4 | Y/N | Y/N/TBC | (fill) | (fill) | Pending |  |
| (fill) | (fill) | #(fill) | D1/2/3/4 | Y/N | Y/N/TBC | (fill) | (fill) | Pending |  |
| (fill) | (fill) | #(fill) | D1/2/3/4 | Y/N | Y/N/TBC | (fill) | (fill) | Pending |  |
| (fill) | (fill) | #(fill) | D1/2/3/4 | Y/N | Y/N/TBC | (fill) | (fill) | Pending |  |

## 23.1 Discovery Questions for Every Team Lead

| # | Question | What It Tells You |
| --- | --- | --- |
| 1 | Do you have Cloud Build pipelines triggered by pushes or PRs on your repos? | D2 flag. Follow up: does it report a status check back to GitHub? |
| 2 | Do any of your Cloud Build pipelines deploy to production or pre-production? | D4 flag. Prod deployment = mission critical. |
| 3 | Is GitHub PR approval used as an approval gate in your change management process? | D4 flag. PR approval as four-eyes control = disruption is a control failure. |
| 4 | Do you publish Python packages, Docker images, or model artifacts from GitHub? | D3 flag. Follow up: which teams consume them? |
| 5 | Do other teams pip install or docker pull from packages your repos publish? | D3 downstream impact. Flag those consuming teams too. |
| 6 | Do any external tools (Jira, monitoring, SonarQube) receive events from your repos? | Webhook inventory. D3 flag if external tools depend on GitHub events. |
| 7 | Do your team members work primarily with Jupyter notebooks and data science scripts? | DS flag. Expect notebook outputs and data files. Targeted comms needed. |
| 8 | Do you commit data files (CSV, pickle, parquet) to GitHub as part of your workflow? | Data file policy impact. Need to discuss alternative workflow before enforcement. |
| 9 | Do you have any planned releases or critical deadlines in the next 4 weeks? | Helps avoid scheduling migration during a critical delivery window. |
| 10 | Who is the business owner for your most critical repo? | D4 only. Required for CAB and change window agreement. |

Your single most important action right now

Before anything else: escalate the Cloud Build question to the platform team.

Ask them directly: has Cloud Build been tested with GitHub EU? Is there a confirmed integration approach?

If no: run the PoC in Phase 0.

Until you have an answer, every D2 team migration date is provisional.

This is the dependency that could delay a significant portion of your migration.